## WMS Agile Project Schedule
Warehouse Stock Inventory System - 8-Week Agile Project Schedule & Gantt
Course: CSE 220 Software Engineering ¦ IAU ¦ Team: Ankit Katwal (Lead), Sabrin Manandhar (Scrum Master), Shivam Khadka (DevOps)
Task / Story ID & Description | Start Date | Duration (Days) | End Date | Refined Duration | Story Points | Assigned Lead | Sprint Phase
Sprint 1 Kickoff & Requirements Elicitation | 2026-07-01 | 2 | 2026-07-02 |  | - | All Members | Sprint 1
WMS-01: User Authentication & Role Access | 2026-07-03 | 4 | 2026-07-06 |  | 2 pts | Ankit Katwal | Sprint 1
WMS-02: Incoming Stock Intake & PO Logging | 2026-07-05 | 6 | 2026-07-10 |  | 5 pts | Shivam Khadka | Sprint 1
WMS-03: Handheld Barcode & QR Scanner | 2026-07-08 | 5 | 2026-07-12 |  | 3 pts | Ankit Katwal | Sprint 1
WMS-04: Real-Time Stock Availability Check | 2026-07-09 | 5 | 2026-07-13 |  | 3 pts | Sabrin Manandhar | Sprint 1
Sprint 1 QA Review & Retrospective | 2026-07-13 | 2 | 2026-07-14 |  | - | All Members | Sprint 1
Sprint 2 Planning & Backlog Refinement | 2026-07-15 | 1 | 2026-07-15 |  | - | All Members | Sprint 2
WMS-05: Low-Stock Watchlist & Threshold Alerts | 2026-07-16 | 5 | 2026-07-20 |  | 3 pts | Sabrin Manandhar | Sprint 2
WMS-06: Urgent Order Priority Tagging | 2026-07-18 | 5 | 2026-07-22 |  | 2 pts | Ankit Katwal | Sprint 2
WMS-07: Atomic Stock Reservation & Locking | 2026-07-20 | 7 | 2026-07-26 |  | 5 pts | Shivam Khadka | Sprint 2
Sprint 2 QA Review & Retrospective | 2026-07-27 | 2 | 2026-07-28 |  | - | All Members | Sprint 2
Sprint 3 Planning & Backlog Refinement | 2026-07-29 | 1 | 2026-07-29 |  | - | All Members | Sprint 3
WMS-08: Supplier Replenishment PO Transmission | 2026-07-30 | 7 | 2026-08-05 |  | 5 pts | Shivam Khadka | Sprint 3
WMS-09: Itemized Dispatch Note Generation | 2026-08-03 | 6 | 2026-08-08 |  | 3 pts | Sabrin Manandhar | Sprint 3
WMS-10: Immutable Audit Transaction Ledger | 2026-08-04 | 6 | 2026-08-09 |  | 3 pts | Ankit Katwal | Sprint 3
Sprint 3 QA Review & Retrospective | 2026-08-10 | 2 | 2026-08-11 |  | - | All Members | Sprint 3
Sprint 4 Planning & Test Matrix Alignment | 2026-08-12 | 1 | 2026-08-12 |  | - | All Members | Sprint 4
Master Test Matrix QA (40 Test Cases) | 2026-08-13 | 6 | 2026-08-18 |  | 40 Cases | Sabrin Manandhar | Sprint 4
GitHub Repo Branch & Pull Request Integration | 2026-08-17 | 5 | 2026-08-21 |  | CI/CD | Shivam Khadka | Sprint 4
Final Project Report Finalization & APA 7 Audit | 2026-08-19 | 6 | 2026-08-24 |  | 100% | All Members | Sprint 4
Final Sprint Review & Deployment Sign-Off | 2026-08-25 | 1 | 2026-08-25 |  | - | All Members | Sprint 4